## Instructions
Using the Status tracker / - At the end of each week, update the status of all activities completed during the week. / - The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week). / - Fill in hours spent on each activity during the current week. / - If 5 team members each spent an hour, that counts as 5 hours. / - Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks. / - During the planning phases, identify the activities to be done during each week. / - If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front). / - For new activities, identify the type of activity - documentation, coordination, estimation etc. / - At the end of each week, plan ahead for the following week Identify people responsible for each activity. / - Estimate the hours needed for the activity / - Error in estimation is calculated using a formula that’s already applied.

PROJECT NUMBER	SSAD XX
PROJECT NAME
PROJECT MENTOR (sponsor)
TEAM MEMBERS	Team Member Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Status
PROJECT NUMBER	21
PROJECT NAME	AR integration with board games
PROJECT MENTOR (sponsor)	Ravi Chandra

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 6- August 12)
Fix meeting with client	Coordination	Abhishek Mathur	0.25	0.25	Done		0	0
GIT Repository setup	Preparation	All	0.25	0.25	Done		0	0
Client meeting	Coordination	All	0.5	0.5	Done		0	0
Learn how to operator Unity3d,Vulforia	Preparation	All	4	3.5	Done		0.5	14.2857142857
Week 2 (August 13 - August 19)
Learn how to recognize 3d objects in unity	Preparation	All	0.5	0.5	Done	Proper documentation not available to integrate Yolo with unity.Cancelled because it is not compatible with all devices.	0	0
Gitlab Structure Setup	Preparation	All	0.25		Done
Team Meeting	Coordination	All	1	1	Done		0	0
Status tracker update	Documentation	Vani Sancheti	0.25	0.25	Done		0	0
Client meeting-1	Coordination	All	0.5	1	Done		-0.5	50
Client meeting-2	Coordination	All	2	2	Done		0	0
Week 3 (August 20 - August 27)
Client meeting-3	Coordination	All	0.75	1	Done		-0.25	25
Methods of project designing discussion	Coordination	All	3	3	Done		0	0
Status tracker update	Documentation	Abhishek Mathur	0.1	0.1	Done		0	0
Present idea for nutrition game with PPT	Preparation	All	0.75	0.5	Done		0.25	50
Explore ideas for other games	Coordination	All	1	1.5	Ongoing		-0.5	33.3333333333
Week 4 (August 28 - September 2)
Client meeting-4	Coordination	All	0.75	0.75	Done		0	0
Prepare a prototype for detecting objects.	Preparation	All	10		Done
Software requirements and specifications	Coordination	All	1	1	Done		0	0
Decide on Usecases for the software	Coordination	All	1	1	Done		0	0
Use case diagram	Preparation	All	0.5	0.5	Done		0	0
Status tracker update	Documentation	Samhita	0.15	0.15	Done		0	0
Week 5 (September 3- September 9)
Prototype for Comparison of objects	Coordination	All	15		Done
UML diagram	Documentation	All	1	1	Done		0	0
Requirements Update	Documentation	All	0.3	0.3	Done		0	0
Status tracker update	Documentation	Samhita	0.15	0.15	Done		0	0
Week 6-7 (September 10- September 23)
Implement basic ideas for initial game	Preparation	Abhishek, Vani	5	8	Done		-3	37.5
Recognition of objects for initial game	Preparation	Abhishek, Vani	3	2	Done		1	50
Perform action on recognized objects for initial game	Preparation	Abhishek, Vani	4	5	Done		-1	20
Status tracker update	Documentation	Abhishek Mathur	0.15	0.15	Done		0	0
Week 8 (September 23- September 30)
Initialize 2nd game	Preparation	Ishita, Samhita	4	5	Done		-1	20
Recognition of objects for second game	Preparation	Ishita, Samhita	3	2	Done		1	50
UI part of 2nd game(INTEGER MAZE)	Preparation	Ishita, Samhita	4	4	Done		0	0
Introducing 3D characters into the board game	Preparation	Ishita, Samhita	5	5	Done		0	0
Status tracker update	Documentation	Abhishek Mathur	0.15	0.15	Done		0	0
Week 9 (October 1- October 8)
Fixing bugs for game made till date	Coordination	All	2	2	Done		0	0
Discussing ideas for further build up	Coordination	All	1.5	1	Done		0.5	50
Status tracker update	Documentation	Abhishek Mathur	0.15	0.15	Done		0	0
Week 10-11 (October 9- October 23)
Tried implementing multiplayer mode for the first game	Coordination	All	10			As there is no proper documentation of integrating multiplayer mode with unity.
3D Board with Snakes And Ladders	Coordination	Ishita, Samhita	5	6	Done		-1	16.6666666667
Design Document	Documentation	All	3	3	Done
Week 12(October 23- October 30)
Tried 3D object detection.	Coordination	All	10			As there is no proper documentation of integrating 3D Integrating software (YOLO)with unity with unity, 3D Object can’t be detected.
Moving the coin to a particular position according to user and checking whether given value is correct or not	Coordination	Vani,Samhita	7	8	Done		-1	12.5
Week 13 (October 30- November 7)
Making of 3D model of sign die	Coordination	Vani,Ishita	2	2	Done		0	0
Making of 3D dice	Coordination	Vani,Samhita	2	2	Done		0	0
Testing of game 1 and game 2	Coordination	All	3	2.5	Done		0.5	20
Fixing remainig bugs	Coordination	All	3	2.5	Done		0.5	20
Adding 3D models in game1	Coordination	Abhishek Mathur	3	2	Done		1	50
Status tracker update	Documentation	Ishita	1	1	Done		0	0